Annual Implementation Report on the Operational Programme Rural Development and Multifunctional Agriculture in the Czech Republic for 2007

CONTENT

1.	SUMMARY	3

2.	INTRODUCTION	3

3.	LegislativE FRAMEWORK OF THE agriculture OP IN THE CR	3

3.1	Summary of relevant legislation and related  programme documents	4

4.	changes of general conditions significant for the implementation of the agriculture op	5

5.	Implementation of priorities and measures in relation to the fulfilment of the agriculture op objectives	6

5.1	Summary of the year 2007	7

5.1.1.	     Receipt of applications	7

5.1.2.	     Reallocation of funds under the Agriculture OP	7

5.1.3.	     Absorption of the remaining financial resources reallocated to Measure 2.1. Rural development within Agriculture OP for the period 2004 – 2006 	8

5.2	Priority I. of the Agriculture OP: “Support to agriculture, processing of agricultural products and to forestry“	9

5.2.1.	Measure 1.1. Investments in agricultural holdings	9

5.2.2.	Measure 1.2. Improving the processing and marketing of agricultural products	10

5.2.3.	Measure 1.3. Forestry	11

5.3	Priority II.: “Rural development, fisheries and vocational training“	14

5.3.1.	Measure 2.1. Promoting the adaptation and development of rural areas	14

5.3.2.	Measure 2.2. Vocational training	18

5.3.3.	Measure 2.3. Fisheries	19

5.4	Priority III. – Technical assistance	21

6.	Financial implementation of assistance	22

6.1	Approved allocation table for the Agriculture OP	22

6.2	Changes in financial flows	22

6.3	Payments	23

7.	Steps taken by the Managing Authority, the intermediaTE body and the monitoring committee to ensure the quality and efficiency of the implementation of assistance	24

7.1	Description of the overall responsibility for management and control	24

7.2	Managing authority	25

7.3	Intermediate body	26

7.4	Measures for monitoring, financial control and evaluation, including data collection mechanisms	26

7.4.1.	Monitoring of the Agriculture OP	26

7.4.2.	Monitoring Committee of the Agriculture OP	28

7.5	Summary of significant problems arisen in the management	30

7.6	Utilisation of technical assistance	30

7.7.	Steps taken to ensure publicity of the Agriculture OP	32

7.7.1.     Publishing	33

7.7.2.     Seminars, conferences	34

8.	Steps taken to ensure compatibility with the community policies and to provide coordination of all community structural assistance	35

9.	brief outlook for the year 2008	35

10.	List of abbreviations	36

11.	List of priorities, measures and investment categories of Agriculture OP	36

12.	Annexes	38

# Summary

The Operational Programme “Rural Development and Multifunctional Agriculture“ successfully entered the year 2007, in the course of which the administration of projects received in 2005 and 2006 continued. In 2007 no more calls for applications were announced due to the drawing down of financial resources and implementation of reallocated funds. The reallocation of unabsorbed funds from 2006 was approved by the Monitoring Committee of the Agriculture OP and subsequently in December 2006 by the European Commission. Decisions concerning the reallocated funds were adopted immediately at the beginning of January 2007 which facilitated the implementation of a number of other successful projects.

In 2007 payments continued to be made to projects assisted under the Operational Programme “Rural Development and Multifunctional Agriculture“ which will also continue in 2008.

The Operational Programme “Rural Development and Multifunctional Agriculture” through some of its measures constitutes a follow up to the aid granted in the framework of SAPARD pre-accession programme. As to the success rate of implementation and absorption of individual measures under Agriculture OP, it is obvious that in the case of measures with which experience had been gained under the SAPARD Programme the use of funds smoothly continued, and a major interest in the aid under these measure has been expressed ever since 2004. As concerns other measures, where it took some time for them to take off the ground, it was only in the 2005-2006 period that the applicants expressed a somewhat stronger interest.

# Introduction

The Annual Implementation Report on the Operational Programme Rural Development and Multifunctional Agriculture (hereinafter referred to as the Agriculture OP) in the Czech Republic for the year 2007 was drawn up by the Managing Authority of the Agriculture OP in cooperation with the State Agriculture Intervention Fund (SAIF – Intermediate Body, Paying Unit) pursuant to Council Regulation (EC) No 1260/1999 laying down general provisions on the Structural Funds. This Annual Implementation Report was discussed/considered and unanimously approved by the Monitoring Committee of the Agriculture OP at its 10th Meeting held in Prague on 28 May 2008.

While drafting the Annual Implementation Report on the Agriculture OP in the Czech Republic for 2007, just like the year before, the Managing Authority proceeded from the requirements as to its content as set out in Article 37 of Council Regulation (EC) No 1260/1999 laying down general provisions on the Structural Funds. It also acted upon the recommendations given by the European Commission.

This report aims to provide a summary of essential information on the implementation and progress of Agriculture OP in the Czech Republic in 2007 and also to present a summary and a description of the situation as of 31 December 2007. For the sake of completeness and in order to provide an overall picture this report also comprises references to some facts and events of 2008.

# Legislative Framework of the Agriculture OP in the CR

The Operational Programme “Rural Development and Multifunctional Agriculture” (No CCI 2003 CZ 06 1 PO 001) is a programme document drafted in the course of the preparation of the Czech Republic for accession to the European Union, within the framework of the new policy concept of rural development for the period following 1 May 2004. It is a follow-up to the assistance granted under the SAPARD Programme and it specifies measures co-financed from the Guidance Section of the European Agricultural Guidance and Guarantee Fund (EAGGF) carried out in areas covered by Objective 1 and measures co-financed from the Financial Instrument for Fisheries Guidance (FIFG).

By the European Commission Decision of 17 June 2004, the Community Support Framework was approved providing for the structural assistance in the Czech Republic. On 2 July 2004, the European Commission also formally approved the Agriculture OP by its Decision No K (2004) 2689. The amount of the Community contribution for the Agriculture OP was determined to be approximately EUR 173 million.

## Summary of relevant legislation and related programme documents

The Agriculture Operational Programme is based on the fundamental documents related to structural policy of the European Union, both at the EU level and the level of the Czech Republic. A comprehensive summary of relevant legal regulations is presented in the programme document.

The following legislation (including all related and implementing regulations) are crucial for the implementation of the Agriculture OP:

Treaty of Accession of the Czech Republic to the European Union,

Resolution of the Government of the CR No 102 of 23 January 2002 on the completion of preparation of programme documents and the designation of the managing and paying authorities for the use of Structural Funds and the Cohesion Fund of the European Union,

Council Regulation (EC) No 1257/1999 of 17 May 1999 on support for rural development from the European Agricultural Guidance and Guarantee Fund (EAGGF) and amending and repealing certain Regulations, as amended,

Council Regulation (EC) No 1260/1999 of 21 June 1999 laying down general provisions on the Structural Funds, as amended,

Council Regulation (EC) No 1263/1999 of 21 June 1999 on the financial instrument for fisheries guidance, as amended,

Act No 563/1991 Coll., on accounting, as amended,

Act No 252/1997 Coll., on agriculture, as amended,

# Act No 218/2000 Coll., on budgetary rules, as amended,

# Act No 100/2001 Coll., on environmental impact assessment, as amended,

Act No 320/2001 Coll., on financial control in public administration and amending certain laws (Act on financial control), as amended,

Act No 40/2004 Coll., on public contracts, as amended,

Act No 137/2006 Coll. on public contracts, as amended.

The Agriculture OP proceeds from the so far adopted national economy strategies and programme documents which define certain priorities for the implementation thereof. They are particularly the following:

# National Development Plan 2004 – 2006,

Community Support Framework Czech Republic 2004-2006 (CCI: 2003CZ161CC001),

# Concept of the policy of the MoA of the Czech Republic,

Position Papers of the MoA and MRD to Chapter 7 and 21 (Agriculture, Economic and social cohesion),

Implementation strategy (covering the field of agriculture and environment).

Simultaneously, the Agriculture OP reflects the needs of individual regions, as specified in Regional Development Plans.

# Changes of General Conditions Significant for the Implementation of the Agriculture OP

The preliminary results of agriculture (according to the Economic Accounts for Agriculture, expressed in constant 2000 prices) indicate a slight increase in agricultural production, particularly the plant production in 2007 compared to 2006. The harvest of cereals rose by 12 %, the rape seed harvest rose by 17 % and the potato harvest by 18 %. Compared to 2006 the plant production increased by 5 % in 2007 and contributed to the overall increase of agricultural production by 3 %. The results of agricultural holdings were substantially influenced by the rise in prices of agricultural producers in 2007. Compared to 2006 these prices rose in cereals by 49 %, in oil seeds by 20 %, in leguminous plants by 40 %, in milk by 4.5 % and in poultry by 10 %. The prices of slaughter cattle and pigs dropped by 2 % and 7.6 % respectively. According to the preliminary results of the Economic Accounts for Agriculture in current prices of 2007, the agricultural production increased by 19 % as compared to the 2006.

The employment in agriculture was on a decline also in 2007, but at a faster rate than in 2006. The number of persons employed in agricultural holdings dropped to 130.4 thousand, which represents a year-on-year drop by 2.7 %. The share of agriculture in the total employment in the national economy of the CR amounted to 2.6 %. There was a year-on-year decline by 0.2  percentage point, namely due to the decrease in the number of persons employed in agriculture, but also due to the increase of the total employment in the national economy. The share of women employed in agriculture (including game keeping and forestry) became stable following a persistent decline and accounted for 30.6 % in 2007.

The rate of unemployment (5.3 %) dropped in the CR by 1.8 percentage point on a year-on-year basis, thus is by 0.7 percentage point lower than the EU-25 average.

There were no more changes in general conditions significant for the implementation of the Agriculture OP.

Table No 1: Basic macro-economic indicators in the CR in the period from 2004 to 2007

| Indicator/year | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- |
| GDP – current prices (CZK million) | 2 781 060 | 2 970 261 | 3 204 086 | 3 557 653 |
| GDP – constant 2000 prices (CZK million) | 2 467 615 | 2 617 608 | 2 776 379 | 2 979 762 |
| Unemployment rate (%) | 8,3 | 7,9 | 7,1 | 5,3 |
| Imports total (CZK million in current prices) | 1 749 095 | 1 829 962 | 2 099 604 | 2 387 395 |
| Exports total (CZK million in current prices) | 1 722 657 | 1 868 586 | 2 143 998 | 2 472 350 |
| Average gross monthly wage, CR total (CZK) | 18 041 | 18 985 | 20 211 | 21 692 |
| Inflation rate* (%) | 2,8 | 1,9 | 2,5 | 2,8 |

*Inflation rate expressed by the increment of the average annual consumer price index, source - CSO

Number of inhabitants: According to the census of inhabitants, houses and apartments carried out in 2001, the total population of the Czech Republic amounts to 10 292 933, of whom 10 223 079 are residents and 69 854 persons with a long-term stay in the territory of the CR. The share of women in the total number of population is 51.2 %.

According to the data provided by the Czech Statistical Office, the total population in 2007 was 10 322 689 inhabitants, of which 5 048 101 men and 5 274 588 women.

Securing the co-financing in the CR for projects implemented under the Agriculture OP

Applicable to the implementation of projects co-financed from the Structural Funds is the principle of additionality. It means that in order to receive the EU funds the CR shall also secure match funding from its national sources. Generally speaking, the EU:CR funds ratio is 75 %:25 %. Based on the regularly drawn up financing plans, the Managing Authority of the Agriculture OP annually forecasts the amount of public expenditure for co-financing of projects implemented under the Agriculture OP. This requirement is subsequently submitted to the Ministry of Finance together with the requirement for the Chapter of Agriculture for the following year. Section 2 of Act No 252/1997 on agriculture, as amended, stipulates that the Ministry of Finance shall commit adequate funds from the state budget so as to secure national co-financing for contributions from the EU Structural Funds.

# Implementation of Priorities and Measures in Relation to the Fulfilment of the Agriculture OP Objectives

The Priority I with its measures Investments in agricultural holdings, Improving the processing and marketing of agricultural products and Forestry in line with the Agriculture OP objectives originally received 60.3 % of the total amount allocated to the programme. Generally, the absorption of funds under Priority I was successful, particularly with respect to Measure 1.1. Investments in agricultural holdings, for which more appropriations were approved at the end of 2006 through the reallocations within the EAGGF and FIFG.

The Priority II, to which originally 38.1 % of the total programme allocation was committed, received additional funds through the reallocation to Sub-measure 2.1.2. Restoring the potential of agricultural landscape and its conservation and 2.1.3. Management of agricultural water resources and providing for their functioning, investment category a) and b) (More details see Chapter 5.1.2. Reallocation of financial resources of the Agriculture OP). The allocation for Sub-measure 2.1.1. Reparcelling, the aim of which is to support the settlement of ownership titles to land, to make spatial and functional adaptations of parcels and to have them demarcated, was fully covered by projects already in 2005.

Under the Agriculture OP the following measures are a follow up to the SAPARD Programme – Measure 1.1. Investments in agricultural holdings, 1.2. Improving the processing and marketing of agricultural products, 2.2. Vocational training, 2.3. Fisheries, and to a large degree also Measure 2.1. Promoting the adaptation and development of rural areas. These measures equal 93 % of the original allocations from public funds for the period 2004-2006.

Detailed summary of individual priorities, measures, sub-measures and investment categories of the Agriculture OP is presented in Chapter 11.

## Summary of the year 2007

# 5.1.1.	Receipt of applications

In 2007 no more calls for applications were announced and activities focused on the control of completed projects, their authorisation and reimbursement of co-financing to aid beneficiaries for successfully implemented projects from the 2005 – 2007 period.

# 5.1.2.	Reallocation of financial resources of the Agriculture OP

The proposed reallocations of financial resources of 2006 allocation in the framework of the Agriculture OP reflected the actual status of the Agriculture OP implementation and the objective of the Ministry of Agriculture to ensure the support to priority measures/sub-measures of this programme (investments in agricultural holdings) and measures essential for sustainable agriculture, forestry and water management (removal of damage caused by floods, preventive anti-flood measures, recovery of agriculture’s production potential, support to landscaping).

These proposals were approved by the Monitoring Committee of the Agriculture OP (in accordance with Council Regulation (EC) No 1260/1999) at its meeting held on 12 and 13 June 2006 in the presence of the DG AGRI and DG FISH representatives. Subsequently these proposals were approved by the members of the Monitoring Committee of the Community Support Framework and later on also by the European Commission through Commission Decision No K (2006) 7276 of 27 December 2006.

At the beginning of January 2007 Decisions were adopted and Conditions were signed up to the amount of approved reallocated funds for projects which were not selected due to overhang of projects (and these projects were included in the pipeline of projects). These projects were registered, satisfied all the eligibility requirements, but at the time of the call for applications there were no funds available for their implementation.

The results of reallocations are the following:

Sub-measure 1.1.1. Investments in agricultural holdings and support for setting up young farmers, investment category a):

36 projects were approved accounting for the total assistance of CZK 109 936 792.

# Sub-measure 2.1.2. Restoring the potential of agricultural landscape and its conservation:

1 project was approved accounting for the total assistance of CZK 2 178 326.

Sub-measure 2.1.3. Management of agricultural water resources and providing for their functioning, investment category a):

12 projects were approved accounting for the total assistance of CZK 57 225 750.

# Sub-measure 2.1.3. Management of agricultural water resources and providing for their functioning, investment category b):

11 projects were approved accounting for the total assistance of CZK 42 121 170.

Altogether the reallocated funds were committed to 60 approved projects in the total amount of CZK 211 464 038.

# 5.1.3.	Absorption of the remaining financial resources reallocated to Measure 2.1. Rural development of the Agriculture OP for the period 2004 - 2006

The ongoing monitoring of drawdown of financial resources within the Agriculture OP performed by the Managing Authority of the Agriculture OP detected that there are available funds within certain measures/sub-measures due to the termination of administration of some projects or a reduction in eligible expenditure in the course of project implementation.

Absorption of the remaining available funds under the Agriculture OP 2004 – 2006 is made possible pursuant to Commission Regulation (EC) No 1320/2006 of 5 September 2006, Title II, Chapter 2, Section 1, Article 4. It is laid down in this article that the Member States may continue, within the current programming period (2000 – 2006), to undertake commitments and make payments from 1 January 2007 to the final date of eligibility for expenditure fixed in the Decisions approving Community support for operational programmes or rural development programming documents, i.e. by 31 December 2008. In this period, however, no commitments can be undertaken for the same measures in the new programming period 2007 – 2013 under the Rural Development Programme (RDP 2007 – 2013), or other programmes.

A thorough analysis of the given situation has shown that the Decisions within the Agriculture OP can be adopted only for the following sub-measures under Measure 2.1. Rural development:

- 2.1.2. Restoring the potential of agricultural landscape and its conservation, removal of damage caused by floods, preventive anti-flood measures

- 2.1.3. Management o agricultural water resources and providing for their functioning, investment category a) Restoration and reconstruction of ponds and agricultural water reservoirs, reconstruction of safety spillways and outlet facilities, including the installations associated with these structures.

In the last call for applications an excessive number of projects was submitted under these sub-measures which satisfied the conditions for approval, but due to the lack of available funds at the time of making the commitments, the Decisions could not be adopted/Conditions could not be signed and the projects thus could not be supported from the Agriculture OP funds.

At the very end of 2007 the Managing Authority of the Agriculture OP approached the applicants whose projects ended up so to say below the line, i.e. could not be financed from the Comunity sources for reasons of lack of financial resources at the time of the last call for applications. Altogether 63 applicants were contacted whose projects had been registered under Sub-measures 2.1.2. and 2.1.3. investment category a) and met the conditions for the adoption of the Decision. At the beginning of 2008 an affirmative response was received from 43 applicants, therefore the Managing Authority of the Agriculture OP in cooperation with the SAIF took immediate steps to ensure the implementation of eligible projects before the end of 2008.

## Priority I of the Agriculture OP: “Support to Agriculture, Processing of Agricultural Products and Forestry“

Priority I of the Agriculture OP is focused on the investments in agricultural holdings, improving the processing and marketing of agricultural products and last but not least on forestry.

### Measure 1.1. Investments in agricultural holdings

Based on the funds reallocated to Measure 1.1. Investments in agricultural holdings, a total of 36 Decisions granting aid were adopted on 8 Jan 2007.

Sub-measure 1.1.1. Investments in agricultural holdings and support for setting up young farmers

Table No 2: Summary of registered applications and adopted Decisions for Sub-measure 1.1.1. Investments in agricultural holdings and support for setting up young farmers – as of 31 Dec 2007

| Sub-measure 1.1.1. | RO SAIF | Total |
| --- | --- | --- |
|  | Pra-gue | České Budějovice | Ústí nad Labem | Hradec Králové | Brno | Olomouc | Opava | No of appli-cations | In thousand CZK |
| Registered Total | 342 | 575 | 155 | 333 | 723 | 323 | 178 | 2629 | 5 498 515 |
| Decisions adopted* | 218 | 370 | 88 | 209 | 487 | 225 | 108 | 1705 | 3 521 530 |
| Reimbursed | 186 | 277 | 75 | 173 | 407 | 201 | 96 | 1415 | 2 613 938 |
| Administra-tion stopped after the adoption of Decisions | 13 | 28 | 7 | 19 | 33 | 16 | 13 | 129 | 278 947 |

*after the deduction of applications the administration of which was stopped

Sub-measure 1.1.2. Further diversification of agricultural activities

Table No 3: Summary of registered applications and adopted Decisions for Sub-measure 1.1.2. Further diversification of agricultural activities – as of 31 Dec 2007

| Sub-measure 1.1.2. | RO SAIF | Total |
| --- | --- | --- |
|  | Prague | České Budějovice | Ústí nad Labem | Hradec Králové | Brno | Olomouc | Opava | No of appli-cations | In thousand CZK |
| Registered Total | 5 | 8 | 1 | 4 | 21 | 5 | 16 | 60 | 38 993 |
| Decisions adopted* | 5 | 6 | 1 | 3 | 15 | 4 | 15 | 49 | 33 200 |
| Reimbursed | 5 | 5 | 1 | 3 | 14 | 4 | 12 | 44 | 30 326 |
| Administra-tion stopped after the adoption of Decisions | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 4 | 2 459 |

*after the deduction of applications the administration of which was stopped

Monitoring indicators of Measure 1.1.

Under Measure 1.1., a total of 1 753 Conditions were signed in the total amount of CZK 3 547 563 thousand.

More details on monitoring indicators are given in Annex 3.

### Measure 1.2. Improving the processing and marketing of agricultural products

Under Measure 1.2., funds are being spent in order to improve the processing of agricultural products, i.e. first and foremost to modernise and reconstruct production facilities, to introduce new technologies as well as to support agricultural products marketing.

Table No 4: Summary of registered applications and adopted Decisions for Sub-measure 1.2. Improving the processing and marketing of agricultural products – as of 31 Dec 2007

| Measure 1.2. | RO SAIF | Total |
| --- | --- | --- |
|  | Prague | České Budějovice | Ústí nad Labem | Hradec Králové | Brno | Olomouc | Opava | No of appli-cations | In thousand CZK |
| Registered Total | 18 | 74 | 12 | 28 | 38 | 21 | 13 | 204 | 771 972 |
| Decisions adopted* | 10 | 52 | 6 | 13 | 10 | 12 | 5 | 108 | 358 454 |
| Reimbursed | 5 | 38 | 3 | 12 | 8 | 9 | 5 | 80 | 233 605 |
| Administra-tion stopped after the adoption of Decisions | 2 | 5 | 2 | 3 | 5 | 2 | 1 | 20 | 110 189 |

*after the deduction of applications the administration of which was stopped

Monitoring indicators of Measure 1.2.

Under Measure 1.2., a total of 108 Conditions were signed in the total amount of CZK 353 256 thousand. More details on monitoring indicators are given in Annex 3.

### Measure 1.3. Forestry

Measure 1.3. is oriented at forestry, especially at good forestry practices in forests associated with the restoring of forestry potential damaged by natural disasters, support for preventive instruments against natural disasters and measures to improve the ecological stability of forests.

In the course of 2007 no calls for applications were announced for Measure 1.3., the applications submitted in the previous years were administered.

The Tables No 5, 6 and 7 clearly indicate the data for Sub-measure 1.3.1. (Restoring forestry potential damaged by natural disasters and fire and introducing appropriate preventive measures), 1.3.2. (Investments in forests) and 1.3.4. (Planting of land not used for farming-afforestation) concerning the registered applications, adopted Decisions, not recommended and not approved applications, or stopped administration of projects as of 31 Dec 2007. Individual data are presented in a breakdown by respective SAIF regional office.

Sub-measure 1.3.1. – Restoring forestry potential damaged by natural disasters and fire and introducing appropriate preventive instruments

Altogether 58 applications were registered. All the applications were recommended and approved and in case of 43 applications the Decision was adopted. Of the total number of 58 applications the administration was stopped in case of 7 projects. Within the transfer of financial resources, proposed and approved in 2006 under the Agriculture OP, a total amount of  EUR 104 593 was reallocated to Sub-measure 1.3.1., of which EUR 83 674 from the EU sources and EUR 20 919 from the state budget of the CR. These amounts were part of the resources from the 2006 allocation for Sub-measure 1.3.4. Planting of and not used for farming (Afforestation), and under Sub-measure 1.3.1. were used primarily for the removal of damage caused by floods in forests, fires and other natural disasters and for introducing appropriate preventive instruments.

Table No 5: Summary of registered applications and adopted Decisions for Sub-measure 1.3.1. Restoring forestry potential damaged by natural disasters and fire and introducing appropriate preventive instruments – as of 31 Dec 2007

| Sub-measure 1.3.1. | RO SAIF | Total |
| --- | --- | --- |
|  | Prague | České Budějovice | Ústí nad Labem | Hradec Králové | Brno | Olomouc | Opava | No of appli-cations | In thousand CZK |
| Registered Total | 2 | 9 | 16 | 4 | 6 | 18 | 3 | 58 | 117 924 |
| Decisions adopted* | 1 | 7 | 11 | 2 | 5 | 17 | 0 | 43 | 86 888 |
| Reimbursed | 0 | 4 | 11 | 1 | 2 | 14 | 0 | 32 | 48 841 |
| Administra-tion stopped after the adoption of Decisions | 0 | 1 | 4 | 0 | 0 | 0 | 2 | 7 | 6 637 |

*after the deduction of applications the administration of which was stopped

Sub-measure 1.3.2. Investments in forests

A total of 133 applications were registered, 109 Decisions were adopted and in 11 cases the administration was stopped.

Table No 6: Summary of registered applications and adopted Decisions for Sub-measure 1.3.2.  Investments in forests – as of 31 Dec 2007

| Sub-measure 1.3.2. | RO SAIF | Total |
| --- | --- | --- |
|  | Prague | České Budějovice | Ústí nad Labem | Hradec Králové | Brno | Olomouc | Opava | No of appli-cations | In thou-sand CZK |
| Registered Total | 16 | 32 | 9 | 21 | 41 | 12 | 2 | 133 | 232 281 |
| Decisions adopted* | 13 | 28 | 5 | 18 | 36 | 9 | 0 | 109 | 191 164 |
| Reimbursed | 13 | 24 | 5 | 18 | 30 | 5 | 0 | 95 | 160 296 |
| Administra-tion stopped after the adoption of Decisions | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 11 | 20 104 |

*after the deduction of applications the administration of which was stopped

Sub-measure 1.3.4. Planting of land not used for farming (Afforestation)

Altogether 19 Decisions were adopted for the total number of 24 registered applications, in three cases the administration was stopped. In the course of reallocation of financial resources, individual amounts were transferred from Sub-measure 1.3.4. in the manner described under Sub-measure 1.3.1.

Table No 7: Summary of registered applications and adopted Decisions for Sub-measure 1.3.4. Planting of land not used for farming (Afforestation) – as of 31 Dec 2007

| Sub-measure 1.3.4. | RO SAIF | Total |
| --- | --- | --- |
|  | Prague | České Budějovice | Ústí nad Labem | Hradec Králové | Brno | Olomouc | Opava | No of appli-cations | In thou-sand CZK |
| Registered Total | 3 | 8 | 1 | 4 | 4 | 3 | 1 | 24 | 7 586 |
| Decisions adopted* | 3 | 5 | 1 | 3 | 3 | 3 | 1 | 19 | 6 912 |
| Reimbursed | 3 | 4 | 1 | 3 | 3 | 3 | 1 | 18 | 5 018 |
| Administra-tion stopped after the adoption of Decisions | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 613 |

*after the deduction of applications the administration of which was stopped

The overview of individual sub-measures of Measure 1.3. suggests that in 2007, just like in the years before, there was no demand for Sub-measure 1.3.3. – Establishment of associations of forest owners on the part of applicants, although under the overall Measure 1.3. an extensive information campaign was held in printed media, in cooperation with NGOs, namely in particular on the occasion of seminars, trade fairs and exhibitions where the Managing Authority of the OP continued to share information on the potential assistance to forestry under the Agriculture OP. Originally, a total of EUR 33 633 was allocated to Sub-measure 1.3.3., of which EUR 23 543 from the EU sources and EUR 10 090 from the state budget of the CR. Due to low interest of applicants and concerns of unabsorption of allocated financial resources, already in 2006 a transfer of funds was proposed and approved within the Agriculture OP to Sub-measure 1.1. Investments in agricultural holdings, where the funds together with other reallocated amounts were spent to reduce the overhang of submitted projects.

Monitoring indicators of Measure 1.3.

As of 31 Dec 2007, a total of 171 Conditions were signed under Measure 1.3., of which under:

Sub-measure 1.3.1. Restoring forestry potential:

43 Conditions were signed in the total amount of CZK 86 598 thousand

Sub-measure 1.3.2. Investments in forests:

109 Conditions were signed in the total amount of CZK 190 771 thousand

Sub-measure 1.3.4. Planting of land not used for farming (Afforestation):

19 Conditions were signed in the total amount of CZK 6 912 thousand.

The total amount of public funds for Measure 1.3. equals CZK 284 281 thousand.

More details on monitoring indicators are given in Annex 3.

## Priority II: “Rural Development, Fisheries and Vocational Training“

The Priority II of the Agriculture OP focuses predominantly on rural development and covers a wide variety of activities.

### Measure 2.1. Promoting the adaptation and development of rural areas

Measure 2.1. comprises five sub-measures which promote reparcelling, restoring the potential of agricultural landscape and its conservation, providing for the functioning of water resources, diversification of agricultural activities and rural development through the LEADER+ type projects.

Sub-measure 2.1.1. Reparcelling

The main purpose of reparcelling is to settle ownership titles to land, to make spatial and functional adaptations of parcels and to have them demarcated. In 2007 no call for applications was announced and no Decisions were adopted for Sub-measure 2.1.1.

Table No 8: Summary of registered applications and adopted Decisions for Sub-measure 2.1.1. Reparcelling – as of 31 Dec 2007

| Sub-measure 2.1.1. | RO SAIF | Total |
| --- | --- | --- |
|  | Prague | České Budějovice | Ústí nad Labem | Hradec Králové | Brno | Olomouc | Opava | No of appli-cations | In thousand CZK |
| Registered Total | 97 | 144 | 31 | 107 | 118 | 51 | 17 | 565 | 1 726 717 |
| Decisions adopted* | 71 | 91 | 29 | 79 | 86 | 37 | 6 | 399 | 1 605 287 |
| Reimbursed | 40 | 71 | 18 | 35 | 61 | 18 | 5 | 248 | 807 953 |
| Administra-tion stopped after the adoption of Decisions | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 295 |

*after the deduction of applications the administration of which was stopped

Sub-measure 2.1.2. Restoring the potential of agricultural landscape and its conservation

As of 31 Dec 2007 a total of 59 Decisions were adopted for Sub-measure 2.1.2. totalling CZK 121 576 thousand. The highest demand for Sub-measure 2.1.2. was reported in the NUTS 2 Southeast region with 56 submitted applications, which represents 65 % of all the applications submitted under this sub-measure. The administration was stopped in case of two projects of the total number of project applications.

Based on the approval of reallocation of funds (by Commission Decision No K (2006) 7276 of 27 December 2006) one more Decision on granting aid from the Agriculture OP for Sub-measure 2.1.2. was adopted in 2007 amounting to CZK 2 178 326.

Table No 9: Summary of registered applications and adopted Decisions for Sub-measure 2.1.2. Restoring the potential of agricultural landscape and its conservation – as of 31 Dec 2007

| Sub-measure 2.1.2. | RO SAIF | Total |
| --- | --- | --- |
|  | Prague | České Budějovice | Ústí nad Labem | Hradec Králové | Brno | Olomouc | Opava | No of appli-cations | In thou-sand CZK |
| Registered Total | 4 | 20 | 4 | 1 | 56 | 0 | 1 | 86 | 165 700 |
| Decisions adopted* | 2 | 11 | 1 | 0 | 45 | 0 | 0 | 59 | 121 576 |
| Reimbursed | 0 | 4 | 0 | 0 | 33 | 0 | 0 | 37 | 72 669 |
| Administra-tion stopped after the adoption of Decisions | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 4 727 |

*after the deduction of applications the administration of which was stopped

Sub-measure 2.1.3. Management of agricultural water resources and providing for their functioning

The highest demand expressed by applicants for Sub-measure 2.1.3. was reported in the NUTS 2 Southeast region – 93 applications (i.e. 39 % of all the submitted applications). The administration was stopped in a total of 11 applications.

Based on the reallocations approved in December 2006, in 2007 a total of 12 Decisions amounting to CZK 57 225 750 were adopted for projects under investment category a) Restoration and reconstruction of ponds and agricultural water reservoirs, and 11 Decisions amounting to CZK 49 621 170 were adopted under investment category b) Procurement and restoration of structures used for amelioration.

Table No 10: Summary of registered applications and adopted Decisions for Sub-measure 2.1.3. Management of agricultural water resources and providing for their functioning – as of 31 Dec 2007

| Sub-measure 2.1.3. | RO SAIF | Total |
| --- | --- | --- |
|  | Prague | České Budějovice | Ústí nad Labem | Hradec Králové | Brno | Olomouc | Opava | No of appli-cations | In thousand CZK |
| Registered Total | 44 | 59 | 10 | 20 | 93 | 8 | 4 | 238 | 1 031 700 |
| Decisions adopted* | 23 | 41 | 7 | 10 | 75 | 1 | 3 | 160 | 715 722 |
| Reimbursed | 18 | 16 | 4 | 6 | 46 | 1 | 1 | 92 | 426 436 |
| Administra-tion stopped after the adoption of Decisions | 3 | 2 | 1 | 1 | 2 | 2 | 0 | 11 | 64 121 |

*after the deduction of applications the administration of which was stopped

# Sub-measure 2.1.4. Rural development (sub-measure of the LEADER+ type)

The implementation of LEADER+ type sub-measure facilitated both the preparation of pilot Local Action Groups, implementation of their integrated development strategies, and the training of other persons with potential interest in the LEADER+ approach, which will continue in the next EU programming period within the Rural Development Programme for 2007-2013

There are three investment categories defined under Sub-measure 2.1.4.. In compliance with the approved Operational Programme Rural Development and Multifunctional Agriculture there were ten Local Action Groups (LAGs) and their strategies selected in 2004 under investment category a). Investment category b) covers specific projects for the implementation of strategies of the selected LAGs with the projects being submitted by the applicants operating in the territory of the respective LAG. Under the investment category c) assistance is granted both to the establishment of new Local Action Groups and to the development of their integrated development strategies.

Since the allocated financial resources were already absorbed, no call for applications was announced in 2007 for investment category c). As of 31 Dec 2007 altogether 71 projects were reimbursed within this investment category amounting to CZK 35 444 thousand.

As concerns investment category b), in 2007 a total of 8 Decisions were adopted within 7 strategies totalling CZK 2 368 345. Thus financial resources were used which were made available particularly because the administration of some projects in individual LAGs was stopped. Therefore it was possible to implement some of the projects selected earlier for which there were no funds available at the time of their selection. As of 31 Dec 2007 a total of 278 projects were reimbursed under investment category b) amounting to CZK 130 165 thousand.

Table No 11: LEADER+ - investment category b), Group 1, Implementation of strategy – as of 31 Dec 2007

| Sub-measure 2.1.4. LEADER+ Investment category b) | RO SZIF | Total |
| --- | --- | --- |
|  | Prague | České Budějovice | Ústí nad Labem | Hradec Králové | Brno | Olomouc | Opava | No of applica-tions | In thou-sand CZK |
| Registered Total | 74 | 113 | 0 | 46 | 57 | 44 | 60 | 394 | 196 050 |
| Decisions adopted* | 63 | 81 | 0 | 36 | 46 | 34 | 40 | 300 | 138 714 |
| Reimbursed | 61 | 72 | 0 | 34 | 44 | 29 | 38 | 278 | 130 165 |
| Administra-tion stopped after the adoption of Decisions | 6 | 16 | 0 | 7 | 3 | 10 | 8 | 50 | 27 995 |

*after the deduction of applications the administration of which was stopped

Table No 12: LEADER+ - investment category c), Group 1, Acquisition of skills – as of 31 Dec 2007

| Sub-measure 2.1.4. LEADER+ Investment category c) | RO SZIF | Total |
| --- | --- | --- |
|  | Pra-gue | České Budějovice | Ústí nad Labem | Hradec Králové | Brno | Olomouc | Opava | No of applica-tions | In thou-sand CZK |
| Registered Total | 14 | 28 | 15 | 24 | 28 | 34 | 6 | 149 | 76 137 |
| Decisions adopted* | 11 | 18 | 5 | 15 | 16 | 15 | 2 | 82 | 42 412 |
| Reimbursed | 9 | 17 | 5 | 14 | 10 | 14 | 2 | 71 | 35 444 |
| Administration stopped after the adoption of Decisions* | 0 | 3 | 2 | 2 | 3 | 1 | 0 | 11 | 5 100 |

*after the deduction of applications the administration of which was stopped

Sub-measure 2.1.5. Diversification of agricultural activities and activities close to agriculture

Table No 13: Summary of registered applications and adopted Decisions for Sub-measure 2.1.5. Diversification of agricultural activities and activities close to agriculture – as of 31 Dec 2007

| Sub-measure 2.1.5. | RO SZIF | Total |
| --- | --- | --- |
|  | Prague | České Budějovice | Ústí nad Labem | Hradec Králové | Brno | Olomouc | Opava | No of applica-tions | In thou-sand CZK |
| Registered Total | 14 | 20 | 10 | 12 | 31 | 12 | 14 | 113 | 93 690 |
| Decisions adopted* | 11 | 10 | 6 | 9 | 18 | 8 | 10 | 72 | 61 218 |
| Reimbursed | 9 | 7 | 2 | 8 | 10 | 5 | 5 | 46 | 36 440 |
| Administration stopped after the adoption of Decisions | 1 | 5 | 3 | 2 | 6 | 3 | 0 | 20 | 17 053 |

*after the deduction of applications the administration of which was stopped

Monitoring indicators of Measure 2.1.

As of 31 Dec 2007 a total of 1 068 Conditions were signed under Measure 2.1., of which under:

Sub-measure 2.1.1. - Reparcelling:

a total of 396 Conditions were signed in the amount of CZK 1 293 617 thousand

Sub-measure 2.1.2. – Restoring the potential of agricultural landscape and its conservation:

a total of 59 Conditions were signed in the amount of CZK 121 533 thousand

Sub-measure 2.1.3. – Management of agricultural water resources and providing for their functioning:

a total of 158 Conditions were signed in the amount of CZK 708 408 thousand

Sub-measure 2.1.4. (a, b, c) – Rural development (LEADER+ type sub-measure):

a total of 383 Conditions were signed in the amount of CZK 181 625 thousand

Sub-measure 2.1.5 Diversification of agricultural activities and activities close to agriculture:

a total of 72 Conditions were signed in the amount of 60 510 thousand

In the framework of the Agriculture OP, the financial assistance paid out under Measure 2.1. totalled CZK 2 365 693 thousand. More details on monitoring indicators are given in Annex 3.

### Measure 2.2. Vocational training

The purpose of vocational training is to provide persons working in the sector of agriculture with access to relevant knowledge, skills and information, and thus increase the competitiveness of their businesses. The seminars are designed for farmers, fishermen, persons working in forestry and processors of products of plant and animal production.

The only applicant under Measure 2.2. Vocational training was the Institute of Agricultural and Food Information (IAFI). In 2004, a call for applications was announced with no deadline set. In the framework of Measure 2.2. Vocational training the Decisions in relation to 2004 allocation were adopted in August 2006 on 8 projects totalling CZK 6 500 500 of support. Funds committed to these projects were paid out in October and November 2006 in the total amount of CZK 6 332 041. With respect to 2005 allocation, following the tender the Decisions were adopted in November 2006 on 16 projects amounting to CZK 10 675 370 of support. Pursuant to the set schedule the payments related to these projects were paid out in October 2007 in the total amount of CZK 9 977 739.

After the approval of reallocation in December 2006 the 2006 allocation was used to support Measure 1.1. Investments in agricultural holdings in 2007.

Table No 14: Summary of registered applications and adopted Decisions for Measure 2.2. Vocational training – as of 31 Dec 2007

| Measure 2.2. | RO SZIF | Total |
| --- | --- | --- |
|  | Prague | České Budějovice | Ústí nad Labem | Hradec Králové | Brno | Olomouc | Opava | No of applica-tions | In thou-sand CZK |
| Registered Total | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 19 405 |
| Decisions adopted* | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 16 310 |
| Reimbursed | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 16 310 |
| Administration stopped after the adoption of Decisions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

*after the deduction of applications the administration of which was stopped

Monitoring indicators of Measure 2.2.

As of 31 Dec 2007 a total of 24 Conditions were signed under Measure 2.2. in the total amount of CZK 16 310 thousand. More details on monitoring indicators are given in Annex 3.

### Measure 2.3. Fisheries

Supporting and improving the fish processing and marketing of fish products, aquaculture and actions by professionals in fisheries are to contribute to the increasing of competitiveness of businesses operated by persons active in the sector of agriculture.

More detailed information on the absorption of funds from the FIFG (covering the entire Measure 2.3. Fisheries and a part of Measure 3.1. financed from the FIFG) is provided in Annex 4, listing all the projects on which the Decisions were adopted, registration number of the application, aid beneficiary, information on the amount for which the Decision was adopted, and information on its payment. The financial amounts are given in EUR.

As of 31 Dec 2007 all the implemented projects under Measure 2.3. were reimbursed and the absorption of the FIFG funds was thus completed.

Low interest expressed by the fishermen community, which is bellow the budget allocated to Measure 2.3. Fisheries, led to the reduction of allocation in the framework of reallocations and is caused by a number of factors. First and foremost by the fact that fisheries sector in the CR is of a fairly small scale and therefore the number of potential beneficiaries is limited. Numerous applicants were repeatedly applying for support regarding many projects and in almost 100% cases they were successful. Since the maximum rate of contribution is 50 % of eligible expenditure, applicants use up all their funds available for investments (depending on the financial standing of the company). Sub-measure 2.3.1. is a follow-up to the SAPARD Programme measures, under which major investments were made, which has an effect on the aid applications submitted by applicants (under currently prevailing conditions – 50% of co-financing).

A number of steps have been taken to achieve better absorption of funds, e.g. repeated extension of eligible expenditure, raising the maximum level of eligible expenditure under Sub-measure 2.3.2., or reallocation of funds from Sub-measure 2.3.1. to Sub-measure 2.3.2., and consistent and on-going updating of the professionals in fisheries on the possibilities of drawing funds from the Agriculture OP. The information on all the actions taken in order to ensure better absorption of funds under Measure 2.3. Fisheries is regularly presented to all members of the Monitoring Committee of the Agriculture OP at the MC meetings. With respect to the level of profitability in fisheries, higher absorption of funds would be encouraged and assisted by a higher rate of public co-financing of projects (this became true in the Operational Programme Fisheries 2007 – 2013, namely up to 60 % of eligible expenditure).

Sub-measure 2.3.1. Fish processing and marketing of fish products

In 2007 no call for applications was announced and no Decision was adopted under Sub-measure 2.3.1. Projects were completed and reimbursed. The largest number of projects was paid out in the Southwest region, followed by the Central Bohemia and Southeast regions.

Table No 15: Summary of registered applications and adopted Decisions for Sub-measure 2.3.1. Fish processing and marketing of fish products – as of 31 Dec 2007

| Sub-measure 2.3.1. | RO SZIF | Total |
| --- | --- | --- |
|  | Prague | České Budějovice | Ústí nad Labem | Hradec Králové | Brno | Olomouc | Opava | No of applica-tions | In thou-sand CZK |
| Registered in 2007 Total | 8 | 7 | 2 | 1 | 5 | 0 | 3 | 26 | 45 900 |
| Decisions adopted* | 6 | 7 | 2 | 1 | 4 | 0 | 3 | 23 | 36 360 |
| Reimbursed | 4 | 5 | 2 | 1 | 4 | 0 | 3 | 19 | 31 156 |
| Administra-tion stopped after the adoption of Decisions | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 5 085 |

*all adopted Decisions

Sub-measure 2.3.2. Aquaculture

In 2007 no call for applications was announced and no Decision was adopted for Sub-measure 2.3.2. Projects were completed and reimbursed. The largest number of projects was paid out in the Southwest and Southeast regions.

Table No 16: Summary of registered applications and adopted Decisions for Sub-measure 2.3.2. Aquaculture – as of 31 Dec 2007

| Sub-measure 2.3.2. | RO SZIF | Total |
| --- | --- | --- |
|  | Prague | České Budějovice | Ústí nad Labem | Hradec Králové | Brno | Olomouc | Opava | No of applica-tions | In thou-sand CZK |
| Registered Total | 7 | 86 | 8 | 8 | 44 | 0 | 4 | 157 | 123 597 |
| Decisions adopted* | 5 | 84 | 8 | 7 | 37 | 0 | 3 | 144 | 110 694 |
| Reimbursed | 4 | 84 | 7 | 6 | 36 | 0 | 3 | 140 | 108 227 |
| Administra-tion stopped after the adoption of Decisions | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 4 | 2 283 |

*all adopted Decisions

Sub-measure 2.3.3. Actions by professionals in fisheries

In 2007 no call for applications was announced and no Decision was adopted for Sub-measure 2.3.3. Projects were completed and reimbursed. The largest number of projects was paid out in the Southwest region.

Table No 17: Summary of registered applications and adopted Decisions for Sub-measure 2.3.3. Actions by professionals in fisheries – as of 31 Dec 2007

| Sub-measure 2.3.2. | RO SZIF | Total |
| --- | --- | --- |
|  | Prague | České Budějovice | Ústí nad Labem | Hradec Králové | Brno | Olomouc | Opava | No of applica-tions | In thou-sand CZK |
| Registered Total | 0 | 20 | 0 | 0 | 3 | 0 | 0 | 23 | 9 723 |
| Decisions adopted* | 0 | 15 | 0 | 0 | 3 | 0 | 0 | 18 | 6 542 |
| Reimbursed | 0 | 13 | 0 | 0 | 3 | 0 | 0 | 16 | 6 026 |
| Administra-tion stopped after the adoption of Decisions | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 490 |

*all adopted Decisions

Due to a slower rate of absorption, the 2006 allocation to Sub-measures 2.3.1., 2.3.2. and 2.3.3. was transferred to projects under Sub-measures 2.1.2. and 2.1.3. for which the Decisions were adopted in 2007.

Monitoring indicators of Measure 2.3.

As of 31 Dec 2007 a total of 175 Conditions were signed (after the deduction of applications the administration of which was stopped) under Measure 2.3., of which under:

Sub-measure 2.3.1. Fish processing and marketing of fish products:

a total of 19 Conditions were signed in the amount of CZK 31 275 thousand

Sub-measure 2.3.2. Aquaculture:

a total of 140 Conditions were signed in the amount of CZK 108 411 thousand

Sub-measure 2.3.3. Actions by professionals in fisheries:

a total of 16 Conditions were signed in the amount of CZK 6 052 thousand.

In the framework of the Agriculture OP, the financial assistance for Measure 2.3. totalling CZK 145 409 thousand was paid out. More details on monitoring indicators are given in Annex 3.

## Priority III – Technical assistance

Priority III aims at the provision of technical assistance in the framework of the Agriculture OP with major emphasis on assisting its effective management, publicity and support to effective evaluation of the Agriculture OP. Detail information on the fulfilment of Measure 3.1. Technical assistance objectives is presented in Chapter 7.6.

# Financial Implementation of Assistance

## Approved allocation table for the Agriculture OP

Table No 18: Current financial allocation – Operational Programme Rural Development and Multifunctional Agriculture

| € 2004 - 2006 | Public expenditure |
| --- | --- |
|  | Public expenditure | EU contribution | CR contribution |
|  |  | EU Total | EAGGF | FIFG |  |
| Support to Agriculture, Processing of Agricultural Products and to Forestry | 153 908 936 | 99 258 276 | 99 258 276 |  | 54 650 660 |
| Investments in agricultural holdings | 128 107 891 | 80 822 075 | 80 822 075 |  | 47 285 816 |
| Improving the processing and marketing of agricultural products | 14 280 179 | 9 996 125 | 9 996 125 |  | 4 284 054 |
| Forestry | 11 520 866 | 8 440 076 | 8 440 076 |  | 3 080 790 |
| Rural Development, Fisheries and Vocational Training | 94 690 665 | 72 901 115 | 68 957 639 | 3 943 476 | 21 789 550 |
| Promoting the adaptation and development of rural areas | 88 202 710 | 68 316 825 | 68 316 825 |  | 19 885 885 |
| Vocational training | 854 418 | 640 814 | 640 814 |  | 213 604 |
| Aquaculture and actions by professionals in fisheries | 5 633 537 | 3 943 476 |  | 3 943 476 | 1 690 061 |
| Technical assistance | 2 322 715 | 1 742 036 | 1 574 439 | 167 597 | 580 679 |
| Technical assistance 3.1 | 2 099 252 | 1 574 439 | 1 574 439 |  | 524 813 |
| Technical assistance 3.2 | 223 463 | 167 597 |  | 167 597 | 55 866 |
| Total | 250 922 316 | 173 901 427 | 169 790 354 | 4 111 073 | 77 020 889 |

The Annex 2 presents the summary financial table for the annual / final implementation report broken down by priority and measure.

## Change in financial flows

Starting from 1 January 2007 based on Government Resolution No 1008 of 30 August 2006 and in line with the Methodology of Financial Flows (under the responsibility of the MoF – National Fund), effective as of 1 January 2007, the MoA introduced to a new system of financial flows, namely the prefinancing of projects from the state budget.

In practice it means that the final beneficiary receives the total amount of support (both the Czech and EU co-financing) from the MoA budget, i.e. from the state budget resources, and only subsequently the Managing Authority Department for the OP requires the MoF to transfer the already paid out amounts of the EU contribution to the MoA account (budgetary chapter administrator). Payments to final beneficiaries are made by the SAIF Financial Unit (the former Paying Unit) based on the right of disposal over the respective MoA account.

## Payments

As of 31 December 2007 a total of 2 720 projects were paid out in the total amount of CZK 4 792 663 027 of public co-financing (the EU contribution accounted for CZK 3 323 631 029). The largest number of projects was paid out within Measure 1.1. Investments in agricultural holdings (1459 projects in the amount of CZK 2 644.2 million of public co-financing), followed by Measure 2.1. Promoting the adaptation and development of rural areas with 782 projects in the amount of CZK 1 526.6 million of public co-financing. The breakdown of paid-out projects by individual measure as of 31 December 2007 is presented in the following table.

Table No 19: Paid out projects as of 31 Dec 2007 in CZK for the 2004 – 2007 period

| Measure | Number of paid-out projects | Public co-financing in CZK | EU contribution to public co-financing in CZK |
| --- | --- | --- | --- |
| 1.1. | 1459 | 2 644 265 183 | 1 686 595 962 |
| 1.2. | 80 | 233 605 033 | 163 523 513 |
| 1.3. | 145 | 214 155 227 | 155 043 631 |
| 2.1. | 782 | 1 526 693 393 | 1 195 280 304 |
| 2.2. | 24 | 16 309 780 | 12 232 329 |
| 2.3. | 175 | 145 409 642 | 101 786 727 |
| 3.1a | 39 | 9 414 795 | 7 061 086 |
| 3.1b | 16 | 2 809 974 | 2 107 477 |
| 3.1. | 55 | 12 224 769 | 9 168 563 |
| Total | 2 720 | 4 792 663 027 | 3 323 631 029 |

In 2007 three certifications took place, namely in the period from 1 Oct 2006 to 30 Apr 2007, from 1 May 2007 to 30 Sep 2007 and from 1 Oct 2007 to 30 Nov 2007. Altogether the amount of EUR 165 555 139.16 was certified as of 31 Dec 2007 (see Table No 20). By the second certification in 2007 the N+2 rule was fulfilled with respect to the EAGGF and 2005 allocation. With the advance payment made by the European Commission included, also the N+2 rule with respect to the FIFG was met by the last 2007 certification.

Table No 20: Certified expenditure as of 31 Dec 2007 for the 2004 – 2007 period

| Measure | Public co-financing in EUR | Total allocation for 2004 – 2006 in EUR | % of certified expenditure of the total allocation |
| --- | --- | --- | --- |
| 1.1. | 88 377 831,46 | 128 107 891 | 68,99 % |
| 1.2. | 6 749 460,35 | 14 280 179 | 47,26 % |
| 1.3. | 7 195 554,85 | 11 520 866 | 62,46 % |
| 2.1. | 56 945 487,54 | 88 202 710 | 64,56 % |
| 2.2. | 582 940,02 | 854 418 | 68,23 % |
| 2.3. | 5 268 247,95 | 5 633 537 | 93,51 % |
| 3.1. | 435 616,99 | 2 322 715 | 18,75 % |
| Total | 165 555 139,16 | 250 922 316 | 65,98 % |

Table No 21: Summary of interim payments received from the EC for the 2005 – 2007 period

|  | EAGGF | FIFG |
| --- | --- | --- |
|  | Date | Amount (EUR) | Date | Amount (EUR) |
| 1st interim payment | Requested | 06.09.05 | 3 649 613,10 | x | x |
|  | Received | 01.12.05 | 3 649 346,00 | x | x |
| 2nd interim payment | Requested | 27.10.05 | 2 860 696,06 | 27.10.05 | 28 367,31 |
|  | Received | 27.12.05 | 2 854 611,00 | 20.12.05 | 28 331,96 |
| 3rd interim payment | Requested | 27.01.06 | 1 699 008,49 | 29.11.05 | 142 124,12 |
|  | Received | 23.02.06 | 1 699 008,00 | 30.12.05 | 142 124,12 |
| 4th interim payment | Requested | 03.04.06 | 5 730 257,00 | 03.04.06 | 106 517,56 |
|  | Received | 11.05.06 | 5 730 257,00 | 29.05.06 | 106 517,56 |
| 5th interim payment | Requested | 13.06.06 | 7 169 173,00 | 13.06.06 | 93 920,28 |
|  | Received | 20.07.06 | 7 169 173,00 | 08.08.06 | 93 920,28 |
| 6th interim payment | Requested | 30.10.06 | 24 857 507,00 | 30.10.06 | 277 461,41 |
|  | Received | 29.11.06 | 24 857 507,00 | 12.12.06 | 277 418,61 |
| 7th interim payment | Requested | 14.06.07 | 29 612 121,00 | 14.06.07 | 587 181,01 |
|  | Received | 16.07.07 | 29 612 121,00 | 31.07.07 | 587 181,01 |
| 8th interim payment | Requested | 29.10.07 | 25 101 739,00 | 29.10.07 | 545 544,23 |
|  | Received | 06.12.07 | 25 101 739,00 | 10.12.07 | 545 544,23 |
| 9th interim payment | Requested | 21.12.07 | 9 816 265,00 | 21.12.07 | 1 169 764,99 |
|  | Received | 05.02.08 | 9 816 265,00 | 18.02.08 | 964 211,34 |
| Total | Requested |  | 110 496 379,65 |  | 2 950 880,91 |
|  | Received |  | 110 490 027,00*) |  | 2 745 249,11**) |

*) Received and requested funds for EAGGF slightly differ because of round down the sums on the part of DG AGRI.

**) Despite the fact that the last payment application claimed the total remaining FIFG amount, the sum paid out did not exceed the 95 % threshold based on Article 32(3) of Council Regulation (EC) 1260/1999.

# Steps Taken by the Managing Authority, the Intermediate Body and the Monitoring Committee to Ensure the Quality and Efficiency of the Implementation of Assistance

## Description of the overall responsibility for management and control

The main principle governing utilisation of funds allocated to the Agriculture OP is a strict separation of the implementation, payment and control functions. Implementation of the Agriculture OP is the responsibility of the Managing Authority of the OP, the ultimate responsibility being born by the Minister of Agriculture. The Managing Authority of the Agriculture OP fulfils its duties pursuant to Article 34 of Council Regulation (EC) No 1260/1999.

The Intermediate Body, i.e. the State Agriculture Intervention Fund (SAIF), participates in the implementation of the Operational Programme, namely on the basis of the Contract on delegating activities between the Managing Authority Department for the OP and the Intermediate Body in meeting the obligations of the Czech Republic arising from the use of funds from Structural Funds of 6 October 2003. The Contract on delegating activities specifies the rights, duties, responsibilities and obligations of the Intermediate Body (SAIF) in implementing the Agriculture OP. The Contract also provides for the possibility to assign ad hoc tasks, which have to be addressed in relation to the implementation of the Agriculture OP.

The following activities were delegated to the SAIF:

- implementation of the Agriculture OP and the Programme Complement,

- setting up an information system for the administration of the Agriculture OP, installation of a software to support the Managing Authority of the OP in its activities,  conducting the administration of the Agriculture OP,

- safeguarding the performance of operative tasks assigned by the Managing Authority of the OP in connection with the implementation of the Agriculture OP,

- provision of data and information necessary for the purposes of monitoring, management and evaluation of the Agriculture OP.

Both the Managing Authority and the Intermediate Body in the management and implementation of assistance under the Agriculture OP shall follow the relevant working procedures (manuals) and methodological guidelines. These documents comply with the effective EU and CR legal regulations.

The Monitoring Committee of the Agriculture OP is set up in order to examine and evaluate the performance of management of the Agriculture OP, to monitor the efficient deployment of funds for implementing the Agriculture OP.

The Internal Audit and Supervision Department at the MoA pursuant to Commission Regulation (EC) No 438/2001 was entrusted with the conduct of sample checks on operations and projects including the system audit.

## Managing Authority

In accordance with Government Resolutions No 102 of 23 January 2002 and No 149 of 12 February 2003 the Ministry of Agriculture of the Czech Republic was designated as the Managing Authority of the Agriculture OP. Pursuant to the Order of the Minister of Agriculture the Managing Authority Department for the Agriculture OP was set up (in 2007 the department was transformed into the Managing Authority Department for the Agriculture OP and OP Fisheries, but in this document it is still reffered to as the Managing Authority for the OP) which performs the activities of the “Managing Authority“. The Managing Authority of the OP is made up of the director and two divisions:

- External Relations Division
b)  Monitoring and Evaluation Division

Tasks to be performed by the Managing Authority are set out in the Rules of Organisation of the MoA and further elaborated on in the guidelines for the implementation of the Agriculture OP in the period 2004 to 2006. The Managing Authority Department for the OP is made up of 12 officers, working in two divisions (each composed of one head and four officers).

# The Organisation chart of the Managing Authority Department for the OP is shown in Annex 5.

## Intermediate Body

Role of the Intermediate Body of the Agriculture OP, to which activities related to the implementation of the Agriculture OP are delegated from the Managing Authority of the Agriculture OP, is performed by the State Agriculture Intervention Fund (SAIF). The SAIF is set up pursuant to Act No 256/2000 Coll., on the State Agriculture Intervention Fund and amendments to some other laws, as amended. The operation and powers of the Fund are provided for by Act No 256/2000 Coll. and Act No 252/1997 Coll., on agriculture, as amended. The SAIF operates under the Ministry of Agriculture and it is a legal entity acting in legal relations on its behalf and under its responsibility. Tasks of the Intermediate Body are defined in the Contract of delegating activities concluded on 6 October 2003.

Under the project of the PA information system implementation at SAIF, conducted by SAP CR, the IS SAP is also used by the Intermediate Body for the administration of Agriculture OP – to be specific the administration of aid applications and control of the Agriculture OP is conducted in SAP CRM using the internal (by SAIF officers) and external (by applicants/beneficiaries) SAIF SAP EP portal and MSSF CENTRAL interface.

Activities of the Intermediate Body of the Agriculture OP at SAIF are carried out by seven regional offices at NUTS level II (in Prague, Brno, České Budějovice, Hradec Králové, Ústí nad Labem, Olomouc and Opava) and by the SAIF Head Office – Department of rural development project measures and Department of control of rural development project measures, which form component parts of programme services. At regional offices of SAIF activities related to the Agriculture OP are performed by the staff of the Division of Financial Support, Division of control of project support and legal experts.

## Measures for monitoring, financial control and evaluation, including data collection mechanisms

### Monitoring of the Agriculture OP

Data for monitoring the Agriculture OP are gathered from applicants via the Aid Applications, further from the Final Implementation Report, attached to the Application for Payment, and is also collected during on-the-spot checks. Further data is generated throughout the administration of aid applications and applications for payment. Data for context indicators as well as some other indicators come from external sources (Czech Statistical Office (CSO), Research Institute of Agricultural Economics (RIAE) and others). Data collection, administration of aid applications and applications for payment and conduct of on-the-spot checks are delegated to the Intermediate Body (SAIF) pursuant to the Contract on delegating activities. The SAIF Financial Unit (formerly the Paying Unit), which is a part of the SAIF structure, executes the payments to final beneficiaries.

Project administration, payments of the Czech national co-financing and monitoring at the level of Intermediate Body and Managing Authority is supported by the SAP Information System (IS SAP), guaranteed by SAIF. Monitoring at the central level in the Czech Republic is supported by the Structural Funds Monitoring System – CENTRAL (MSSF – CENTRAL), guaranteed by the Ministry for Rural Development. Payments and accounting of the EU co-financing is supported by the VIOLA system, guaranteed by the Ministry of Finance. Data between the IS SAP and MSSF – CENTRAL is communicated bi-directionally via interface. Monitoring outputs serve as a basis for drafting the annual and final implementation reports.

# Annexes 1, 3 and 4 comprise monitoring tables with data as of 31 December 2007.

Evaluation of results of the priority axis Community Support Framework “Rural Development and Multifunctional Agriculture“ (see Table 23). Indicator values based on the paid-out projects are zero in 2004, since in that year no project was paid out yet.

Table No 22: Indicators of priority axis Community Support Framework: Rural Development and Multifunctional Agriculture

| Indicator | Unit of measure-ment | Baseline value (2001, unless stated otherwise) | 2004 | 2005 | 2006 | 2007 | Target value | Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Impact indicators |
| Agricultural export (class 0, 1, 4, SITS, rev. 3) | billion CZK billion EUR FOB | 42,581 1,339 | 57,134 1,796 | 72,764 2,445 | 76,475 2,569 | 89,742 3,251 | 53,976 1,697 | CSO |
| Gross agricultural output | billion CZK in 1989 constant prices | 76,041 | 77,260 | 73,558 | 70,500 | 70,100 (estimate) | 75,998 | CSO |
| Registered rate of unemployment in rural areas | % | 7,1 (2001) 7,6 (2003) | 8,1 | 7,6 | 7,4 | 6,8 (estimate) | 6,5 | CSO MoLSA |
| Result indicators |
| Gross agricultural output per employee in agriculture | thousand CZK in 1989 constant prices | 438,3 | 493,2 | 486,7 | 476,8 | 474,2 (estimate) | 768,8 | CSO |
| Gross number of created jobs | Number of jobs | 0 | 0 | 45 | 110 | 1 522 | 5 000 | OP RDMA |
| Output indicators |
| Number of supported applicants | Number of persons | 0 | 0 | 299 | 972 | 1 401 | 2 500 | OP RDMA |
| Number of supported projects | Number of projects | 0 | 0 | 356 | 1 566 | 2 794 | 3 000 | OP RDMA |
| Total eligible expenditure of supported projects | Share of covered expenditure in total allocation (%) | - | 0 | 7,17 | 43,64 | 66,7 | 80 | OP RDMA |
| Involvement of private sector | Realised private co-financing in EUR | 0 | 0 | 24 748 617 | 84 946 814 | 166 781 514 | 142 677 696 | OP RDMA |

The development of impact indicators suggests changes in the rural sector. In the course of the monitored period the Agricultural export was growing (class 0,1,4 SITC rev. 4 are given for the year 2007), while the gross agricultural output has been on a decline since 2004. The registered rate of unemployment in rural areas has not been available in the CSO or MoLSA database since 2006, hence it is not included.

The 2007 value of the Gross agricultural output per employee in agriculture result indicator is just an estimate since at the time of preparation of the Annual Implementation Report its value was not known yet, similarly as the value of the Gross agricultural output. The time series of the Gross agricultural output per employee in agriculture indicator was appropriately adjusted to reflect the changed methodology of monitoring.

The second result indicator is the Gross number of created jobs. Though the value of this indicator was showing an upward trend, but its target value has not been attained as yet.

The output indicators of this priority axis are being successfully fulfilled. The Number of supported applicants was growing throughout the period, however the target value was not achieved. The Number of supported projects almost reached the target value. As the 2007 values of both the indicators clearly show, there are on average almost 2 supported projects per one supported applicant. The Total eligible expenditure accounts for almost 67 % of the allocation. The value of the Involvement of private sector exceeded the target value, namely by EUR 24 103 818.

### Monitoring Committee of the Agriculture OP

In accordance with Article 35 of Council Regulation (EC) No 1260/1999 of 21 June 1999, laying down general provisions on the Structural Funds, the Minister of Agriculture established the Monitoring Committee of the Operational Programme “Rural Development and Multifunctional Agriculture” (MC of the Agriculture OP) to ensure monitoring and evaluation of the implementation of the Operational Programme “Rural Development and Multifunctional Agriculture“, monitoring of effective use of funds and correct implementation of programmes and projects supported under EU Structural Funds.

The Statute and the Rules of Procedure of the MC of the Agriculture OP were approved at the 1st Meeting of the MC of the Agriculture OP on 10 December 2003 and came into force upon the signature of the Minister of Agriculture on 12 January 2004.

The MC of the Agriculture OP is made up of 26 members appointed by the Minister of Agriculture (representatives of both the governmental and non-governmental institutions) and the same number of substitutes. Its membership reflects the make-up of the National SAPARD Monitoring Committee. Meetings of the MC of the Agriculture OP are, apart from its regular members, regularly attended also by the European Commission representatives, acting as observers. The MC of the Agriculture OP adopts decisions based on the principle of consensus.

Since its establishment the MC of the Agriculture OP has been meeting twice a year and has periodically been monitoring the implementation of the Agriculture OP in the Czech Republic.

Within the MC of the Agriculture OP there are Working Groups established on individual measures under the Agriculture OP composed of the members of the MC of the Agriculture OP. The task of the Working Groups is to discuss documents prepared for the respective meetings of the Monitoring Committee. Meetings of Working Groups are governed by the Rules for Working Groups of 23 November 2004. Apart from the MC of the Agriculture OP members the Working Groups meetings are also attended by the Managing Authority staff, representatives of the MoA technical services or other experts, where appropriate. Conclusions are drawn based on consensus.

#### 8th Meeting of the MC of the Agriculture OP

The 8th meeting of the Monitoring Committee of the Agriculture Operational Programme was held in the conference room of the Ministry of Agriculture on 21 May 2007. The meeting was chaired by Prof. Ing. Magdalena Hrabánková, CSc., the chairperson of the Committee, together with Mgr. Miroslav Daněk, the director of the Managing Authority Department for the OP. The topics on the agenda were the following:

- Progress Report on the current status and implementation of the Agriculture OP

- Report on the implementation of measure 3.1. – Technical Assistance (project plans of the TA for the remaining period were confirmed)

- Report on Publicity of the Agriculture OP

- Annual Implementation Report on the Agriculture Operational Programme  in the CR for 2006

- Information on the current status of preparation of the OP Fisheries for the 2007 – 2013 period

- Information on the Ex-post evaluation of the SAPARD Programme in the Czech Republic

#### 9th Meeting of the MC of the Agriculture OP

The 9th meeting of the Monitoring Committee of the Agriculture Operational Programme was held in the conference room of the Ministry of Agriculture on 21 November 2007. The meeting was chaired by Prof. Ing. Magdalena Hrabánková, CSc., the chairperson of the Committee, together with Mgr. Miroslav Daněk, the director of the Managing Authority Department for the OP. The topics on the agenda were the following:

- Progress Report on the current status and implementation of the Agriculture OP

- Report on the implementation of Measure 3.1. – Technical Assistance

- Report on Publicity of the Agriculture OP

- Information on the Ex-post evaluation of the SAPARD Programme in the Czech Republic – approval of the final report of the Ex-post evaluation

- Information on the phytocenologic monitoring in the territory of five pilot PLAs of the  SAPARD programme  – description of final status

- Information on the current status of preparation of the OP Fisheries for the 2007 – 2013 period.

In 2007 no written procedures were held within the MC of the Agriculture OP in relation to the Agriculture OP implementation. The written procedure was used only for the sake of approval of the minutes of the 8th and 9th meetings of the MC of the Agriculture OP.

## Summary of Significant Problems Arisen in the Management

The audits carried out by the Audit and Supervision Department of the MoA in 2007 focused on the verification of the compliance with the set out activities and procedures on the part of the Managing Authority Department for the Agriculture OP and the SAIF Intermediate Body. The results of audits did not state any serious deficiencies.

In the course of 2007 no major problems arose in the Agriculture OP management.

## Utilisation of Technical Assistance

Project applications under Measure 3.1. Technical assistance are submitted by the Managing Authority Department for the OP which is also responsible for the implementation of this measure. The framework plan of drawing technical assistance is annually submitted to the MC of the Agriculture OP for consideration and approval. The approval of partial eligible expenditure is the responsibility of the chairperson of the Monitoring Committee of the Agriculture OP.

In 2007 altogether 10 projects were registered totalling CZK 2 432 750, of which a total of 9 projects under the European Agricultural Guidance and Guarantee Fund (EAGGF) in the total amount of CZK 2 332 790 and 1 project under the Financial Instrument for Fisheries Guidance (FIFG) in the total amount of CZK 99 960. The summary of adopted Decisions, concluded Conditions (including Addenda to the Conditions) and submitted Applications for payment is presented in Table No 23.

Table No 23: Summary of adopted Decisions, concluded Conditions and submitted Applications for payment for 2007 as of 31 December 2007

| Adopted Decisions | Concluded Conditions | Submitted Applications for payment |
| --- | --- | --- |
| Number / Total amount in CZK of which the EU share in CZK | Number / Total amount in CZK of which the EU share in CZK | Number / Total amount in CZK of which the EU share in CZK |
| EAGGF | FIFG | EAGGF | FIFG | EAGGF | FIFG |
| 9 / 2 332790 EU: 1 749 592 | 1 / 99 960 EU: 74 970 | 9 / 1 649 655 EU: 1 237 237 | 1 / 87 274 EU: 65 455 | 9 / 1 652 052 EU: 1 239 035 | 3 / 460 354 EU: 345 265 |
| Total 10 / 2 432 750 EU: 1 824 562 | Total 10 / 1 736 929 EU: 1 302 692 | Total 12 / 2 112 406 EU: 1 584 300 |

In the field of monitoring and management the following projects were implemented:

- Drafting and publishing the Annual Implementation Report on the Operational Programme “Rural Development and Multifunctional Agriculture“ for the year 2006 in the circulation of 1 500 copies;

- The 8th and the 9th Meeting of the Monitoring Committee of the Agriculture Operational Programme;

- One project related to the technical support for the Managing Authority of the OP (Secretariat for the Monitoring Committee of the Agriculture OP).

Another field is the evaluation of Agriculture Operational Programme. It covers particularly the analyses and evaluations of the Agriculture OP. In 2007, an expert analysis of Measure 2.3. Fisheries of the Operational Programme “Rural Development and Multifunctional Agriculture” was conducted.

In relation to the preparation of the next programming period the following projects were completed under Measure 3.1. Technical assistance under the FIFG:

- Drafting the methodology "Pond management with regime improving the quality of aquatic environment" in the framework of preparation of the next programming period 2007-2013 – FIFG;

- Translation of the National Strategic Plan, Operational Programme Fisheries and Ex ante evaluation into the English language under the FIFG.

The so called communication measures/activities cover apart from other things publishing of various information materials. The Managing Authority of the OP published a map illustrating the distribution of 10 Local Action Groups within the territory of the CR under the LEADER +, two brochures presenting the examples of projects implemented under the Agriculture OP by individual NUTS 2 cohesion regions, and a couple of promotional merchandise such as diaries and calendars. All of the above mentioned information materials were distributed among potential applicants for aid under the Agriculture OP at trade fairs, exhibitions, seminars and other information events. The information materials are also available in the lobby of the MoA which is freely accessible by the general public. They were also distributed through the intermediary of the individual Regional Offices and the Head Office of the State Agriculture Intervention Fund (SAIF).

During 2007 in the framework of educational events, a project was implemented called Seminars (trainings) and workshops focused on the education and training of the Managing Authority staff with respect to the next programming period and the potential exchange of experience with foreign partners, the first part of which was devoted to the exchange of experience with the Slovak partners within the Rural Development Programme of the Slovak Republic. The second part of the project consisted of a 2 day module focused on improving the presentation skills of individual officers of the Managing Authority. All the trained participants were awarded a final certificate. Altogether 17 participants were trained in the first part of the project and altogether 11 participants were trained in its second part.

The Managing Authority of the OP in cooperation with the Association for Rural Renewal provided for the presentation of successful Local Action Groups or their activities in the exhibition hall F3 at the International exhibition Země Živitelka in České Budějovice. The rent for the exhibition space of 168 m2 was covered from the Agriculture Operational Programme.

Table No 24: Summary of individual areas under Measure 3.1 Technical assistance of the Agriculture Operational Programme – Source: Submitted Applications for payment as of 31 Dec 2007 (Graphics are included in Annex 6)

| Name of the area under Measure 3.1. Technical assistance | Areas of implemented activities | Number of implemented projects | Public co-financing Total in CZK |
| --- | --- | --- | --- |
| Area of monitoring and management | Drawing up and printing of Annual Reports | 4 | 545 101 |
|  | Technical support to the MA OP and the Secretariat of the MC OP | 4 | 880 274 |
|  | Organisation of the MC OP meeting | 5 | 473 782 |
| Area of evaluation | Analyses and evaluation | 7 | 3 499 091 |
|  | Preparation of programme documents for the period 2007-2013 | 6 | 1 591 854 |
| Area of communication measures/activities | Organisation of seminars and workshops | 6 | 1 346 679 |
|  | Presentation at trade fairs and exhibitions | 2 | 528 190 |
|  | Publishing of information brochures | 4 | 908 993 |
|  | Publishing of information leaflets | 3 | 150 024 |
|  | Publishing and printing of the Rules for applicants | 4 | 446 716 |
|  | Other publicity measures | 10 | 1 854 065 |
| Total |  | 55 | 12 224 769 |

Note.: 1) The indicated area of implemented activities comprises projects covering more areas of implemented activities in one project, e.g. the Rules for applicants, information leaflets and other activities from the other publicity measures (e.g. promotional merchandise). Altogether there are two projects of this type.

More information on publicity activities are presented in Chapter 7.7.

## 7.7. Steps Taken to Ensure the Publicity of the Agriculture OP

Publicity and information dissemination is the responsibility of the Managing Authority of the OP pursuant to the Communication Action Plan, approved as a component part of the Programme Complement by the Monitoring Committee of the Agriculture OP on 11 August 2004. The Communication Action Plan is implemented through annual publicity plans. For the reasons of limited publicity needs of the Agriculture OP in the period from 2007 to 2008 (the calls for applications were no more announced) there are no more annual publicity plans prepared for this period.

Communication activities under the Agriculture OP are periodically monitored (namely through monthly CSF monitoring reports). Staff involved in the communication related activities under the OP and CSF receive updated information on activities at periodically held meetings of the Information and Publicity Working Group.

### 7.7.1. Publishing activities

Based on the carried out audit of communication activities (for more details see the Annual Implementation Report on the Operational Programme Agriculture for 2006) the Managing Authority of the OP was recommended to pay more attention to the presentation of successfully implemented projects funded from the Agriculture OP. With respect to this fact, in May 2007 the Brochure of successfully implemented projects funded from the Agriculture OP was published in the circulation of 10 000 copies with the view to highlight the benefits of using the EU financial resources for the Czech agriculture and rural areas. This project was implemented in collaboration with the State Agriculture Intervention Fund which through its individual RO SAIF supplied supporting materials (successfully implemented projects). The referred to brochure also comprises ten examples of model projects which in more detail describe selected implemented activities within the Operational Programme Agriculture.

Also another brochure was published in the A5 format (in the circulation of 2 700 copies) pinpointing the results of Sub-measure 2.1.4. Rural development (LEADER+ type sub-measure), which presents several selected projects under individual strategies of the 10 Local Action Groups. This project was implemented in collaboration with the State Agriculture Intervention Fund which through its individual Regional Offices supplied supporting materials (implemented projects), and in cooperation with the individual Local Action Groups which also provided the photo documentation and other materials to be published. The above referred to brochure was complemented by a folded map called Distribution of LAGs within the territory of the CR which defines the territory of  LAGs in graphics, gives an overall description of their strategies and presents a list of contact data for individual LAGs. The map was published in a bilingual (Czech and English) version in the circulation of 3 500 copies.

Both these publications, including the map, were highly appreciated by both the general and professional public and also by potential applicants under the Rural Development Programme and the Operational Programme Fisheries to whom they are offered as motivating and encouraging materials.

In August 2007 the Czech-English version of the Annual Implementation Report on the Operational Programme Rural Development and Multifunctional Agriculture in the Czech Republic for 2006 was published in the circulation of 1 500 copies.

All the publications and brochures were funded from Measure 3.1 Technical Assistance of the Agriculture Operational Programme.

The Managing Authority Department for the OP in cooperation with the Communication Department of the Ministry of Agriculture of the CR publishes press releases on the latest developments and answers technical inquiries raised by the general public. All the information on the Agriculture OP is made available on the website of the Ministry of Agriculture www.mze.cz under the icon of Support from the EU and national aid in the section of Agriculture Operational Programme, and also on the website of the State Agriculture Intervention Fund www.szif.cz in the section of  Operational Programme Rural Development and Multifunctional Agriculture (RDMA) and on the website of the Ministry for Regional Development www.strukturalni-fondy.cz in the section of Structural Funds / Operational Programmes / Rural Development and Multifunctional Agriculture. All those interested from among the community of non-governmental non-profit organisations are pursuant to Government Resolution No 1232/2003 also supplied with the information in an electronic form. In 2007 this means of communication was exploited to a lower degree than in the period where aid applications under the Agriculture OP were received.

Advisory services to applicants as well as the general public are also rendered on an ongoing basis by seven Regional Offices of SAIF and, where necessary, also by the SAIF Head Office.

For further publicity of the Agriculture OP, also the merchandise bearing the MoA logo was used provided by the Communication Department of the MoA. Moreover in 2007 the OP own merchandise was supplied such as diaries and calendars. This merchandise was distributed by the Managing Authority of the OP among the professional public either through the Head Office and ROs of SAIF, or directly on the occasion of exhibitions, trade fairs, seminars and conferences where the Agriculture OP is presented.

### 7.7.2. Seminars, conferences

In 2007, the Managing Authority Department for the OP presented the Operational Programme Agriculture and individual measures at technical exhibitions, trade fairs, seminars and conferences. More details on individual presentations are given in Table 25 below.

Table No 25: Seminars, conferences related to the Agriculture OP – 2007

| Date | Name and description | Venue |
| --- | --- | --- |
| 23–28 Aug 2007 | Presentation of the Agriculture OP at Země živitelka 2007 exhibition | České Budějovice |
| 23–28 Aug 2007 | Presentation of Sub-measure 2.1.4. or results of Local Action Groups within the LEADER initiative at Země živitelka 2006 exhibition (Association for Rural Renewal together with the MoA) | České Budějovice |
| 12 Nov 2007 | Publicity of the Agriculture OP at a seminar focused on the Rural Development Programme – Vysočina | Jihlava |
| 13-14 Nov 2007 | Publicity of the Agriculture OP at the National Conference on Rural Areas | Boskovice |
| 15 Nov 2007 | Presentation of the Agriculture OP at a seminar of the Ministry of Agriculture on the use of support under the Rural Development Programme – a case study from Agriculture OP | Brno |
| 27 Nov 2007 | Presentation of the Agriculture OP at a seminar of the Ministry of Agriculture on use of support under the Rural Development Programme – a case study from Agriculture OP | Opava |
| 28 Nov 2007 | Presentation of the Agriculture OP at a seminar of the Ministry of Agriculture on use of support under the Rural Development Programme – a case study from Agriculture OP | Olomouc |
| 29 Nov 2007 | Presentation of the Agriculture OP at a seminar of the Ministry of Agriculture on use of support under the Rural Development Programme – a case study from Agriculture OP | Hradec Králové |
| 3 Dec 2007 | Presentation of the Agriculture OP at a seminar of the Ministry of Agriculture on use of support under the Rural Development Programme – a case study from Agriculture OP | České Budějovice |
| 6 Dec 2007 | Presentation of the Agriculture OP at a seminar of the Ministry of Agriculture on use of support under the Rural Development Programme – a case study from Agriculture OP | Prague |
| 10 Dec 2007 | Presentation of the Agriculture OP at a seminar of the Ministry of Agriculture on use of support under the Rural Development Programme – a case study from Agriculture OP | Ústí nad Labem |
| 15 Dec 2007 | Publicity of the Agriculture OP at the conference Working Saturday of Mayors | Prague |

# 8.	Steps Taken to Ensure the Compatibility with the Community Policies and to Provide Coordination of All Community Structural Assistance

The Managing Authority declares, that throughout the implementation of the Operational Programme “Rural Development and Multifunctional Agriculture“, the duty is observed to ensure compatibility with Community policies, namely with respect to the protection of environment and support to equal opportunities between men and women.

Entrusted with the coordination of Community structural assistance granted to the Czech Republic was the Ministry for Regional Development, the Community Support Framework Department. The Monitoring Committee of the Community Support Framework (MC of the CSF) was set up to monitor and supervise the CSF implementation and evaluate the progress made in the attainment of its goals. The MC of the CSF was established upon the Decision of the Minister for Regional Development No 25/2004 of 27 February 2004. By the same decision also the Statute of the MC of the CSF was approved. Members of the MC of the CSF are regularly updated on the progress of the Agriculture OP implementation at the MC of the CSF meetings.

For the purposes of operative management of Structural Funds in the CR the Advisory Committee of the Community Support Framework was established. It meets at monthly intervals and its membership, apart from the director of the Managing Authority of the Community Support Framework, is also composed of the directors of the Managing Authorities of individual operational programmes, a representative of the National Fund – Paying and Certifying Authority (MoF department). The Community Support Framework issues guidelines for the application of Community and national rules.

# 9.	Brief Outlook for the Year 2008

At the end of February 2008 additional Decisions were adopted for projects under the Agriculture OP measures in which funds were made available (mostly from projects rejected during the administration) and in which there is no risk of duplicity of funding under the other EU programmes for the 2007 – 2013 period.

These are projects under Sub-measure 2.1.2. Restoring the potential of agricultural landscape and its conservation and 2.1.3. Management of agricultural water resources and providing for their functioning – investment category a) Restoration and reconstruction of ponds and agricultural water reservoirs.

These projects shall be implemented in such a way for the aid beneficiaries to receive the financial assistance from the Agriculture OP no later than by 31 Dec 2008, i.e. by the final date for eligibility of expenditure set out in the Commission Decision on granting assistance to Agriculture OP.

# 10.	List of Abbreviations

AA and LO – Agrarian Agency and Land Office

Agriculture OP – Operational Programme “Rural Development and Multifunctional

Agriculture“

EAGGF – European Agriculture Guidance and Guarantee Fund

EC – European Commission

EU – European Union

FIFG – Financial Instrument for Fisheries Guidance

GDP – Gross Domestic Product

# HO SAIF – Head Office of the State Agriculture Intervention Fund

LAG – Local Action Group

LEADER+ - Community initiative for rural development

MA of the OP – Managing Authority of the Operational Programme Agriculture

MC of the Agriculture OP – Monitoring Committee of the Operational Programme “Rural Development and Multifunctional Agriculture”

MC of the CSF – Monitoring Committee of the Community Support Framework

MoA – Ministry of Agriculture of the Czech Republic

NUTS – Nomenclature of Territorial Statistical Units

OP Fisheries – Operational Programme Fisheries

RIC – Regional Information Centre

RO SAIF – Regional Office of the State Agriculture Intervention Fund

SAPARD – Special Pre-Accession Programme for Agriculture and Rural Development

SAIF – State Agriculture Intervention Fund

# 11.	List of Priorities, Measures, Sub-measures and Investment Categories of the Agriculture OP

# Priority I Support to Agriculture, Processing of Agricultural Products and to Forestry

## Investments in agricultural holdings

###### 1.1.1 Investments in agricultural holdings and support for setting up young farmers

| a) | Rationalisation and reconstruction of existing facilities for the keeping of cattle, pigs, sheep and goats |  |
| --- | --- | --- |
| b) | Rationalisation and reconstruction of existing facilities for the keeping of laying hens |  |  |  |
| c) | Improving the storage of slurry and farm manure |  |  |  |  |
| d) | Investments in the reconstruction and technologies for the storage of fruit and vegetables |  |  |
| e) | Machinery for agricultural production |  |  |  |  |  |  |
| f) | Investments in the reconstruction / construction of storage capacities for cereals and oil seeds; investments in technologies for post-harvest treatment, assessment and storage of cereals and oil seeds |  |  |  |  |  |  |

###### 1.1.2 Further diversification of agricultural activities

| a) | Production, processing and direct sale of agricultural products |  |  |  |
| --- | --- | --- | --- | --- |
| b) | Production, processing and marketing of non-food agricultural products |  |
| c) | Production, processing and marketing of biomass made of one’s own agricultural activity |

## Improving the processing and marketing of agricultural products

| a) | Improving the processing of meat (including poultry) and edible offal |  |  |  |
| --- | --- | --- | --- | --- |
| b) | Improving the processing of milk and milk (dairy) products |  |  |  |  |
| c) | Improving the processing of edible fruits (including nuts) and vegetables |  |  |  |
| d) | Improving the processing of milling industry products |  |  |  |  |
| e) | Improving the processing of starch |  |  |  |  |  |  |

## Forestry

###### 1.3.1 Restoring forestry potential damaged by natural disasters and fire and introducing appropriate preventive

###### instruments

| a) | * Protective measures designed to prevent or mitigate damage caused by disasters in forests in G24, extraordinary measures at disasters caused by biotic and abiotic agents, i.e. predominantly insect and fungal pests (e.g. sawfly, bark beetle, totrix, geometric moth, etc.), wood-destroying fungi (needle blight, etc.), climatic and other factors (common protection and prevention are not applicable) at large-area applications, * reconstruction of damaged forest vegetation, * forest regeneration following salvage felling, |
| --- | --- |
| b) | * Preventive anti-flood measures on small watercourses and in their catchment areas, and anti-erosion measures, * Removal of damage caused by floods on small watercourses and in their catchment areas, removal of erosion furrows and gullies. |

###### 1.3.2 Investments in forests

| a) | Construction, reconstruction or modernisation of forest transport network, |
| --- | --- |
| b) | Construction, reconstruction or modernisation of facilities regulating water regime (amelioration, retention basins, etc.), |
| c) | Support for activities leading to regulation of the number of forest visitors and providing for their safety, within which especially the following will be supported (construction of trails for tourists, including bike trails, facilities along them providing for visitors’ safety, e.g. bridges, handrails, steps, parking space, resting places, shelters, forest springs, information panels, etc.), |
| d) | Purchase of machines and equipment to maintain and repair forest roads, paths and trails, to maintain and clean water bodies, watercourses and amelioration networks, and purchase of environmentally friendly technologies used in forestry. |

###### 1.3.3 Establishment of associations of forest owners

| a) | Expenditure to furnish the necessary offices and to equip them for the association’s work, including computers, and expenditure to purchase equipment which is connected with the services that the association will provide to its members for a minimum period of the upcoming five years, |
| --- | --- |

###### 1.3.4 Planting  of land not used for farming (Afforestation)

| a) | Planting of land not used for farming and maintenance of young planted forest stands until these are secured. |
| --- | --- |

# Priority II Rural Development, Fisheries and Vocational Training

## 2.1 	Promoting the adaptation and development of rural areas

###### 2.1.1 Reparcelling

| a) | Surveying work to design a reparcelling proposal, land survey in order to identify owned parcels and to demarcate newly designed parcels based on the approved reparcelling design, |
| --- | --- |
| b) | Implementation of common reparcelling facilities (i.e. field roads, anti-erosion measures, measures to increase the ecological stability of the landscape (local Territorial System of Ecological Stability including subsequent maintenance of the TSES components)). |

###### 2.1.2 Restoring the potential of agricultural landscape and its conservation

| a) | Recovery of agriculture’s production potential, |
| --- | --- |
| b) | Flood prevention |

###### 2.1.3 Management of agricultural water resources and providing for their functioning

| a) | Restoration and reconstruction of ponds and agricultural water reservoirs, reconstruction of safety spillways and outlet facilities including the installations associated with these structures (these ponds and agricultural water reservoirs do not serve for fish farming business), |
| --- | --- |
| b) | Procurement and restoration of structures used for amelioration (structures to irrigate or drain). |

###### 2.1.4 Rural development (sub-measure of the LEADER+ type)

| b) | Group 1 – strategy implementation – project applicant |
| --- | --- |
| c) | Group 2 – acquisition of skills |

###### 2.1.5 Diversification of agricultural activities and activities close to agriculture

| a) | Construction, reconstruction, modernisation and furnishing of facilities for agri-tourism, facilities and equipment for leisure activities, |
| --- | --- |
| b) | Diversification of agricultural activities and activities close to agriculture to provide multiple activities or alternative income, |
| c) | Support for the use of alternative sources of energy – investments in the utilisation of alternative sources of energy (max. 5 MW). |

## 2.2 	Vocational Training

| a) | Provision and implementation of training activities including consultations and practise in compliance with the support objective. |
| --- | --- |

## 2.3	 Fisheries

###### 2.3.1 Fish processing and marketing of fish products

| a) | Construction of new processing facilities or reconstruction of the existing ones so that the operation can comply with the production, public health and sanitary requirements according to EU standards and modernisation or purchase of new fish processing technologies. |
| --- | --- |

###### 2.3.2 Aquaculture

| a) | Increasing the production capacity of aquaculture (construction of new units and/or extension of existing ones), and modernisation of existing aquaculture facilities. |
| --- | --- |

###### 2.3.3 Actions by professionals in fisheries and promotion measures

| a) | Setting-up producers’ organisations, |
| --- | --- |
| b) | Reduction of pathological risks in aquaculture, |
| c) | Support to identify new outlets. |

# Priority III Technical Assistance

## 3.1. Technical assistance

| a) | Management, implementation, monitoring and control of operations of the Guidance Section of the EAGGF and FIFG |
| --- | --- |
| b) | Other expenditure for technical assistance |

# 12. Annexes

# Annex 1 – Standard monitoring table as of 31 December 2007

Annex 2 – Financial table for the Annual/Final Implementation Report broken down by

priority and measure

Annex 3 – Common indicator tables for monitoring of the Rural Development Programme                    2000-2006(I) – English version only

Annex 4 – “Progress Report on the Programme” table – monitoring the absorption of funds from

the FIFG

# Annex 5 – Organisation chart of the Managing Authority Department for the OP

Annex 6 – Graphics of individual areas of Measure 3.1. Technical assistance

_________________________

i allocations are calculated using the DG BUDGET exchange rate for December 2007: 26.38 CZK/EUR

(I)  IS SAP source with the reference to the summary of Conditions as of 31 December 2007

A current allocation means the allocation after the execution of transfer of financial resources approved both at the level of the MC and the EC.

PŘÍLOHY

ANNEXES

# Footnotes

Average registered number of employees (actual persons) in agricultural primary production holdings excluding the related services and game keeping, preliminary data.

Source: Registered number of employees and their wages in the CR for the 1st – 4th quarter of 2006, 2007, CSO 2007, 2008.

Source: Employment and unemployment in the CR according to the results of LFSS (4th quarter of 2006, 2007), CSO 2007, 2008.  Starting from 2006 the source includes data from agriculture, game keeping and forestry.

# Text boxes

1)